[ AURIXA SYSTEMS ]. Build funding structure Aurixa Systems Construction Finance Report Lot 148, Riverbend Estate — how the build is funded, what it costs while it is building, and the position at completion. STAGED; IDC MODELLED.

| Prepared for | J. & S. Nguyen | Client reference | CL-2026-0418 |
| --- | --- | --- | --- |
| Prepared by | A. Nguyen | Date of issue | 31 July 2026 |
| Document reference | APR-0418-01 | Version | 1.0 |

01  Funding summary

The headline structure

| LAND FACILITY | BUILD FACILITY | TOTAL FACILITY | INTEREST DURING BUILD |
| --- | --- | --- | --- |
| $267,280 80% of $334,100 | $360,320 80% of $450,400 | $627,600 80% of on-completion value | $14,860 44 weeks, capitalised |

02  Structure

The facilities

Facility structure

| Facility | Purpose | Limit | Rate | Type | Term | Repayment |
| --- | --- | --- | --- | --- | --- | --- |
| Land | Settle the land contract | $267,280 | 6.34% | Variable | 30 years | Interest only during build |
| Construction | Fund progress claims | $360,320 | 6.54% | Variable | 30 years | Interest only on drawn balance |
| Total |  | $627,600 | 6.45% |  |  |  |

Interest is charged only on the drawn balance of the construction facility, so the effective cost during the build is far below the full limit.

03  Drawdown schedule

Staged against build progress

Progress drawdown schedule

| Week 0 |  | Land settlement — $267,280 Land facility fully drawn · cumulative $267,280 |
| --- | --- | --- |
| Week 4 |  | Deposit — $22,520 5% of build contract · cumulative $289,800 |
| Week 10 |  | Base stage — $67,560 15% on slab · cumulative $357,360 |
| Week 20 |  | Frame stage — $90,080 20% on frame · cumulative $447,440 |
| Week 32 |  | Lock-up — $112,600 25% at lock-up · cumulative $560,040 |
| Week 40 |  | Fixing — $90,080 20% at fixing · cumulative $650,120 |
| Week 44 |  | Completion — $67,560 15% on practical completion · cumulative $717,680 |

04  Interest during construction

What it costs to build

Interest during construction

| Stage | Weeks | Drawn balance | Rate | Interest | Cumulative |
| --- | --- | --- | --- | --- | --- |
| Land only | 0–4 | $267,280 | 6.34% | $1,304 | $1,304 |
| Deposit drawn | 4–10 | $289,800 | 6.42% | $2,146 | $3,450 |
| Base stage | 10–20 | $357,360 | 6.45% | $4,433 | $7,883 |
| Frame stage | 20–32 | $447,440 | 6.47% | $6,680 | $14,563 |
| Lock-up | 32–40 | $560,040 | 6.49% | $5,592 | $20,155 |
| Fixing to completion | 40–44 | $650,120 | 6.50% | $3,251 | $23,406 |
| Total interest during construction | 44 |  |  | $23,406 |  |

Interest is capitalised into the facility rather than paid monthly, so no cash contribution is required during the build. The capitalised amount increases the balance at completion.

05  Completion position

Where you land

Position at practical completion

| Item | Amount | Note |
| --- | --- | --- |
| Land price | $334,100 | Settled at week 0 |
| Build contract | $450,400 | Including upgrades |
| Interest during construction | $23,406 | Capitalised |
| Total cost | $807,906 | Excluding acquisition costs |
| On-completion valuation | $743,000 | Estimate — see the package assessment |
| Debt at completion | $651,006 | Facility plus capitalised interest |
| LVR at completion | 87.6% | Against the on-completion valuation |
| Cash contributed | $156,900 | Deposit and acquisition costs |
| Equity at completion | $91,994 | Value less debt |

An LVR of 87.6% against the on-completion valuation exceeds the 80% assumed when the facility was structured. This is the direct consequence of the package being priced above comparable completed stock, and it will require either LMI or an additional cash contribution at completion.

06  Conditions precedent

Before each drawdown

Conditions precedent

|  | Item | Owner | Due | Status |
| --- | --- | --- | --- | --- |
| ☐ | Executed fixed-price building contract, signed by both parties. | {{task.owner}} | {{task.due}} |  |
| ☐ | Builder's public liability and construction works insurance, current. | {{task.owner}} | {{task.due}} |  |
| ☐ | Home warranty insurance certificate. | {{task.owner}} | {{task.due}} |  |
| ☐ | Council-approved plans and the construction certificate. | {{task.owner}} | {{task.due}} |  |
| ☐ | Lot registration confirmed and title issued. | {{task.owner}} | {{task.due}} |  |
| ☐ | Progress claim certified by the lender's valuer before each drawdown. | {{task.owner}} | {{task.due}} |  |
| ☐ | Final occupation certificate before the completion drawdown. | {{task.owner}} | {{task.due}} |  |

07  Risks

What could go wrong

Risks

| Risk | Severity | Mitigation |
| --- | --- | --- |
| LVR at completion exceeds 80% | ▲ HIGH | At 87.6% the lender will require LMI of approximately $19,400 or a further $59,000 cash contribution. Resolve this before signing the build contract, not at completion. |
| Build overruns the 44-week programme | ▲ MEDIUM | Each additional month adds approximately $3,500 of capitalised interest and $2,250 of rent forgone. Liquidated damages of $180 a week recover only part. |
| Cost overrun on provisional sums | ▲ MEDIUM | $23,800 of provisional sums and prime cost items are not fixed. Any overrun is a cash contribution, not a further drawdown, unless the facility is increased. |
| Registration delay pushes out the fixed-price period | ▲ HIGH | The build price is fixed for 180 days. If registration slips beyond that the builder may reprice, and the facility was sized on the current price. |
| Builder insolvency | ▲ LOW | Home warranty insurance covers completion but not delay. Confirm the builder's financial standing before the first drawdown. |

08  Next steps

From approval to first drawdown

| 1 | Resolve LVR | Address the completion-LVR shortfall before signing the build contract. |
| --- | --- | --- |
| 2 | Approve | Formal approval issued on both facilities. |
| 3 | Settle land | Land facility drawn; title transferred. |
| 4 | Satisfy CPs | Provide the conditions precedent listed in section six. |
| 5 | First claim | Deposit drawdown released to the builder. |

Important information

Disclaimer, privacy and terms

Disclaimer

This document has been prepared for the named recipient only and is general in nature. It does not take into account any person's objectives, financial situation or needs, and it is not financial product, credit, tax or legal advice. Obtain your own professional advice before acting on it.

Privacy

Personal information collected in connection with this document is handled in accordance with our privacy policy and applicable privacy law. It is used only for the purposes described in this document and for related compliance and record-keeping obligations.

Terms of use

This document remains our property and is provided in confidence. It may not be reproduced, forwarded or relied upon by any person other than the named recipient without our written consent.