[ AURIXA SYSTEMS ]. Residual land value & profitability Aurixa Systems Development Feasibility Report 18–22 Sample Road, Marrickville — a 24-apartment scheme tested for profitability, funding and sensitivity. 24 UNITS; RESIDUAL LV; STRESS-TESTED.

| Prepared for | J. & S. Nguyen | Client reference | CL-2026-0418 |
| --- | --- | --- | --- |
| Prepared by | A. Nguyen | Date of issue | 31 July 2026 |
| Document reference | APR-0418-01 | Version | 1.0 |

Contents

01    Executive summary

02    Feasibility metrics

03    Assumptions

04    Scheme & yield

05    Revenue

06    Costs

07    Funding & cash flow

08    Programme

09    Sensitivity analysis

10    Risks & mitigations

11    Conclusion

A    Full model

01  Executive summary

Does the scheme work

Executive summary The scheme returns 17.4% on cost at a land price of $4.2m — above hurdle, but only 2.4 points above, and the margin is thin to construction cost. On the assumptions in section three, a 24-apartment scheme produces a gross realisation of $22.8m against a total development cost of $19.4m, a development profit of $3.38m and a margin on cost of 17.4%. The residual land value at a 20% hurdle is $3.72m against an asking price of $4.2m. The scheme therefore works at the hurdle only if the land is acquired below the asking price, or if construction comes in below the $4,180 per square metre allowed. Neither is unreasonable, but both are required. Sensitivity is dominated by construction cost. A 5% increase — well inside the range seen in the last three years — removes $640,000 of profit and takes the margin on cost to 14.1%, below hurdle. What this means › Margin on cost of 17.4% against a 20% hurdle at the asking land price. › Residual land value at hurdle is $3.72m; the asking price is $4.2m. › A 5% construction cost increase takes the scheme below hurdle. › Do not proceed at the asking price without a fixed-price build contract.

02  Feasibility metrics

The headline outcome

| RESIDUAL LAND VALUE | DEVELOPMENT PROFIT | MARGIN ON COST | PROJECT IRR |
| --- | --- | --- | --- |
| $3.72m At 20% hurdle | $3.38m At asking land price | 17.4% Hurdle 20% | 21.8% Ungeared, 30 months |

03  Assumptions

Every input, with its basis and date

Feasibility assumptions Land price; $4,200,000 — asking; Scheme; 24 apartments over 4 levels. Saleable area; 2,184 m²; Construction rate; $4,180/m² GFA — QS advice. Professional fees; 9.5% of construction; Statutory contributions; $1,140,000 — s7.11. Contingency; 5% of construction; Selling costs; 3.2% of gross realisation. Finance rate; 8.95% — senior debt; LVR / LCR; 65% of GRV. Programme; 30 months to final settlement; Hurdle; 20% margin on cost. Construction rate is from a quantity surveyor's elemental estimate dated 18 July 2026. Contributions are from the council's current contributions plan and are subject to indexation at the date of the construction certificate.

04  Scheme & yield

What is being built

Product mix and yield

| Product | Count | Avg area m² | Total area m² | Rate $/m² | Avg price | Gross realisation |
| --- | --- | --- | --- | --- | --- | --- |
| 1 bed | 6 | 58 | 348 | $10,200 | $591,600 | $3,549,600 |
| 2 bed | 12 | 88 | 1,056 | $10,600 | $932,800 | $11,193,600 |
| 2 bed + study | 4 | 104 | 416 | $10,800 | $1,123,200 | $4,492,800 |
| 3 bed | 2 | 182 | 364 | $10,300 | $1,874,600 | $3,749,200 |
| Total | 24 | 91 | 2,184 | $10,440 |  | $22,985,200 |

Rates are from comparable off-the-plan sales in the precinct over the last nine months, adjusted for level, aspect and completion date.

05  Revenue

Gross realisation

Revenue

| Item | Basis | Amount |
| --- | --- | --- |
| Apartment sales | 24 units per the mix above | $22,985,200 |
| Car space sales | 8 surplus spaces at $65,000 | $520,000 |
| Storage cage sales | 18 cages at $12,000 | $216,000 |
| Less selling and marketing | 3.2% of gross realisation | -$758,000 |
| Less GST — margin scheme | Estimated | -$1,412,000 |
| Net realisation |  | $21,551,200 |

06  Costs

Every line, grouped

Development costs

| Group | Item | Basis | Amount |
| --- | --- | --- | --- |
| Acquisition | Land | Asking price | $4,200,000 |
| Acquisition | Stamp duty and legals | NSW | $232,000 |
| Construction | Building works | 2,940 m² GFA at $4,180 | $12,289,200 |
| Construction | Contingency | 5% of construction | $614,460 |
| Professional | Design and consultants | 9.5% of construction | $1,167,474 |
| Professional | Project management | 1.5% of construction | $184,338 |
| Statutory | Section 7.11 contributions | Council plan | $1,140,000 |
| Statutory | Authority and certification | Estimate | $186,000 |
| Finance | Interest and line fees | 8.95%, 30 months | $1,284,000 |
| Holding | Rates, insurance, security | 30 months | $96,000 |
|  | Total development cost |  | $21,393,472 |

Construction is 57% of total cost, which is why the sensitivity in section nine is dominated by the build rate.

07  Funding & cash flow

Drawdown against programme

Debt drawdown and repayment against programme [ AREA CHART ] {{funding.series}}

30 months, peak debt $11.4m   ·   Source: Aurixa feasibility model   ·   Alt text: Debt peaks at $11.4m in month 24 and is repaid from settlements between months 27 and 30

Funding structure

| Facility | Limit | Rate | Drawn at peak | Purpose |
| --- | --- | --- | --- | --- |
| Land facility | $2,730,000 | 8.45% | $2,730,000 | 65% of land price |
| Construction facility | $9,940,000 | 8.95% | $8,670,000 | Progress claims |
| Peak debt | $12,670,000 |  | $11,400,000 |  |

Peak debt of $11.4m is 49.6% of gross realisation and 53.3% of total development cost, both inside typical senior-debt parameters.

08  Programme

Acquisition to final settlement

Development programme

| Month 0 |  | Land settlement Land facility drawn; DA lodged |
| --- | --- | --- |
| Month 7 |  | Development consent Assumed; 7-month assessment |
| Month 9 |  | Construction certificate Contributions paid on CC |
| Month 10 |  | Construction commences 44-week build programme |
| Month 12 |  | Sales launch Off-the-plan; 60% pre-sale target |
| Month 24 |  | Practical completion Peak debt $11.4m |
| Month 26 |  | Occupation certificate Strata registration |
| Month 27 |  | Settlements commence Debt repayment begins |
| Month 30 |  | Final settlement Facility discharged |

09  Sensitivity analysis

The three inputs that matter

Sensitivity

|  | Base | Build +5% | Revenue −5% | Programme +6 mths | Upside |
| --- | --- | --- | --- | --- | --- |
| Total cost | $21.39m | $22.03m | $21.39m | $21.65m | $21.39m |
| Net realisation | $21.55m | $21.55m | $20.47m | $21.55m | $22.63m |
| Development profit | $3.38m | $2.74m | $2.30m | $3.12m | $4.46m |
| Margin on cost | 17.4% | 14.1% | 11.8% | 16.0% | 22.9% |
| Against 20% hurdle | Below | Below | Below | Below | Above |
| Residual land value | $3.72m | $3.12m | $2.68m | $3.48m | $4.74m |

10  Risks & mitigations

What could break it

Risks & mitigations

| Risk | Severity | Mitigation |
| --- | --- | --- |
| Construction cost exceeds the QS estimate | ▲ HIGH | Construction is 57% of cost and a 5% overrun takes the scheme below hurdle. Do not proceed without a fixed-price design-and-construct contract. |
| Planning consent takes longer than seven months or is refused | ▲ HIGH | Make the land contract conditional on development consent, or price the land at the unconditional discount. |
| Pre-sale target of 60% is not met | ▲ MEDIUM | Senior debt is conditional on pre-sales. Model a six-month delay and confirm the facility permits it. |
| Apartment values soften before settlement | ▲ MEDIUM | A 5% fall removes $1.08m of profit. Off-the-plan contracts transfer some of this risk but increase settlement default exposure. |
| Statutory contributions are indexed upward before CC | ▲ LOW | $1.14m is indexed quarterly. Budget a 4% increase and pay early where permitted. |

11  Conclusion

Proceed, revise or abandon

CONCLUSION CONFIDENCE: HIGH Proceed only at a land price at or below $3,720,000 and with a fixed-price construction contract. Do not proceed at the $4,200,000 asking price on a cost-plus build. The scheme is viable but the margin is thin, and the thinness is entirely attributable to two variables that can both be fixed contractually: the land price and the build rate. Fixing both converts a marginal feasibility into a sound one. Fixing neither leaves a 17.4% margin exposed to a construction market that has moved more than 5% in each of the last three years. Next steps 1. Offer $3,720,000 for the land, conditional on development consent. 2. Tender the build as fixed-price design and construct before committing. 3. Confirm the senior debt facility permits a six-month pre-sale delay. 4. Re-run this feasibility on the tendered build price before settlement.

APPENDIX A

Full model

Line-level model output supporting the summaries above.

| Line | Description | Quantity | Rate | Amount |
| --- | --- | --- | --- | --- |
| 1.01 | Land acquisition | 1 | $4,200,000 | $4,200,000 |
| 1.02 | Transfer duty | 1 | $232,000 | $232,000 |
| 2.01 | Demolition and site preparation | 1 | $186,000 | $186,000 |
| 2.02 | Substructure | 2,940 m² | $412 | $1,211,280 |
| 2.03 | Superstructure | 2,940 m² | $1,860 | $5,468,400 |
| 2.04 | Fit-out and finishes | 2,940 m² | $1,240 | $3,645,600 |
| 2.05 | Services | 2,940 m² | $560 | $1,646,400 |
| 2.06 | External works and landscaping | 1 | $131,520 | $131,520 |

Important information

Disclaimer, privacy and terms

Disclaimer

This document has been prepared for the named recipient only and is general in nature. It does not take into account any person's objectives, financial situation or needs, and it is not financial product, credit, tax or legal advice. Obtain your own professional advice before acting on it.

Privacy

Personal information collected in connection with this document is handled in accordance with our privacy policy and applicable privacy law. It is used only for the purposes described in this document and for related compliance and record-keeping obligations.

Terms of use

This document remains our property and is provided in confidence. It may not be reproduced, forwarded or relied upon by any person other than the named recipient without our written consent.