[ COVER IMAGE — 1600 × 900 px minimum ] Builder render — Facade B

[ AURIXA SYSTEMS ]. Turnkey package assessment Aurixa Systems House & Land Package Assessment Lot 148, Riverbend Estate — land, build contract, inclusions, staged payments and the completed-value position. ASSESSED; CONTRACT REVIEWED.

| Prepared for | J. & S. Nguyen | Client reference | CL-2026-0418 |
| --- | --- | --- | --- |
| Prepared by | A. Nguyen | Date of issue | 31 July 2026 |
| Document reference | APR-0418-01 | Version | 1.0 |

| 01 | Summary & verdict Does the package stack up |
| --- | --- |

Executive summary The package is priced $41,000 above comparable completed stock and should be renegotiated before contract. The land and build together total $784,500. Three comparable completed dwellings of similar size in the same estate have sold between $726,000 and $752,000 in the last six months, which puts the package roughly 5.5% above the completed market. The gap is concentrated in the upgrade schedule. $38,400 of upgrades has been added to a base contract of $412,000, and only about half of that spend is recoverable in a valuation. Registration is the other exposure. The lot is not registered and the estimated registration date has already moved twice. A build cannot start before registration, and the fixed-price period on the build contract runs for only 180 days. What this means › Package is $41,000 above comparable completed stock. › $38,400 of upgrades; approximately half is recoverable at valuation. › Lot registration has slipped twice; the build price is fixed for 180 days only. › Recommend renegotiating the upgrade schedule before signing.

| 02 | Package metrics The headline numbers |
| --- | --- |

| LAND | BUILD | TOTAL | COMPLETED VALUE |
| --- | --- | --- | --- |
| $334,100 Lot 148, 448 m² | $450,400 Incl. upgrades | $784,500 Excl. acquisition costs | $743,000 Est. — comparables |

| 03 | Land The lot |
| --- | --- |

Lot particulars Lot and estate; Lot 148, Riverbend Estate, Stage 6; Land area; 448 m². Frontage; 12.5 m; Orientation; Rear north-east. Registration status; Unregistered; Estimated registration; Q2 2027 — revised twice. Fall across the lot; 1.4 m — site costs allowed; Covenants; Design covenant; facade approval required. Easements; Drainage easement, 1.0 m rear; Land price; $334,100.

| 04 | Build contract What is being contracted |
| --- | --- |

Contract terms

| Element | Position | Assessment |
| --- | --- | --- |
| Contract type | Fixed price, HIA new homes | Standard; no amendments sought |
| Base contract | $412,000 | Market rate for the floor plan |
| Upgrades | $38,400 | Approximately half recoverable at valuation |
| Fixed-price period | 180 days from signing | Expires before the estimated registration date |
| Build period | 44 weeks from slab | Standard for the builder |
| Liquidated damages | $180 per week | Below the market rent forgone of $520 |
| Provisional sums | $14,200 — site costs | Not fixed; exposure if the fall is worse than surveyed |
| Prime cost items | $9,600 — fixtures | Allowances are below the display level |

Provisional sums and prime cost items are estimates, not fixed prices. Together they represent $23,800 of open exposure.

| 05 | Inclusions & upgrades Line by line |
| --- | --- |

Upgrade schedule

| Item | Category | Included | Upgrade cost | Recoverable |
| --- | --- | --- | --- | --- |
| Ducted air conditioning | Comfort | No | $9,800 | High |
| Stone benchtops throughout | Kitchen | 40mm base | $6,200 | High |
| Upgraded appliance package | Kitchen | Base package | $4,400 | Medium |
| Floor tiles to living areas | Flooring | Carpet base | $5,600 | Medium |
| Landscaping and driveway | External | No | $7,200 | High |
| Fencing | External | No | $3,400 | High |
| Facade upgrade — Facade B | External | Facade A | $1,800 | Low |
| Total upgrades |  |  | $38,400 |  |

'Recoverable' is our assessment of how much of each upgrade a valuer would reflect in the completed value. Landscaping, fencing and air conditioning recover well; facade and appliance upgrades generally do not.

| 06 | Payment schedule Staged against build progress |
| --- | --- |

Progress payment schedule

| On signing |  | Deposit — 5% $22,520 · cumulative $22,520 |
| --- | --- | --- |
| Slab |  | Base stage — 15% $67,560 · cumulative $90,080 |
| Frame |  | Frame stage — 20% $90,080 · cumulative $180,160 |
| Lock-up |  | Lock-up stage — 25% $112,600 · cumulative $292,760 |
| Fixing |  | Fixing stage — 20% $90,080 · cumulative $382,840 |
| Completion |  | Final — 15% $67,560 · cumulative $450,400 |

| 07 | Completed value Against comparable stock |
| --- | --- |

Package against comparable completed stock

|  | This package | 14 Riverbend Dr | 27 Willow Way | 8 Elm Court |
| --- | --- | --- | --- | --- |
| Status | To be built | Sold Jun 2026 | Sold Apr 2026 | Sold Feb 2026 |
| Land | 448 m² | 462 m² | 441 m² | 455 m² |
| Building | 198 m² | 204 m² | 191 m² | 202 m² |
| Accommodation | 4 · 2 · 2 | 4 · 2 · 2 | 4 · 2 · 2 | 4 · 2 · 2 |
| Price | $784,500 | $752,000 | $726,000 | $741,000 |
| Landscaped | Included | Yes | Yes | Yes |
| Age at sale | New | 2 years | 1 year | 3 years |

Completed-value assessment

| Basis | Value | Method |
| --- | --- | --- |
| Comparable median | $741,000 | Median of three comparable sales |
| Adjusted for building area | $743,000 | Adjusted to 198 m² |
| Package price | $784,500 | Land plus build plus upgrades |
| Variance | −$41,500 | Package above adjusted comparable value |

| 08 | Risks & mitigations What could go wrong |
| --- | --- |

Risks & mitigations

| Risk | Severity | Mitigation |
| --- | --- | --- |
| Registration slips again and the fixed-price period expires | ▲ HIGH | Negotiate a fixed-price period tied to registration rather than to signing, or a price-rise cap of CPI. |
| Valuation at completion comes in below the package price | ▲ HIGH | A $41,500 shortfall would require additional cash at settlement. Obtain an 'as if complete' valuation before signing. |
| Provisional sums and prime cost items exceed allowances | ▲ MEDIUM | $23,800 of open exposure. Request a fixed site-cost quote after a full geotechnical report. |
| Build overruns and liquidated damages under-compensate | ▲ MEDIUM | LDs are $180/week against $520/week of rent forgone. Seek an increase or budget the difference. |

| 09 | Recommendation Proceed, renegotiate or decline |
| --- | --- |

RECOMMENDATION CONFIDENCE: HIGH Renegotiate before signing. Remove or reprice the low-recovery upgrades, tie the fixed-price period to registration, and obtain an 'as if complete' valuation. The package is sound in structure and the builder is reputable. The problem is price, and it is concentrated in a $38,400 upgrade schedule that a valuer will only partly recognise. Removing the facade and appliance upgrades alone closes roughly $6,200 of the gap at no practical cost to the finished dwelling. Next steps 1. Remove the facade upgrade and revert the appliance package to base. 2. Request a fixed-price period tied to registration, not to signing. 3. Obtain an 'as if complete' valuation before the cooling-off period expires. 4. Request a fixed site-cost quote following a geotechnical report.

|  | Important information Disclaimer, privacy and terms |
| --- | --- |

Disclaimer

This document has been prepared for the named recipient only and is general in nature. It does not take into account any person's objectives, financial situation or needs, and it is not financial product, credit, tax or legal advice. Obtain your own professional advice before acting on it.

Privacy

Personal information collected in connection with this document is handled in accordance with our privacy policy and applicable privacy law. It is used only for the purposes described in this document and for related compliance and record-keeping obligations.

Terms of use

This document remains our property and is provided in confidence. It may not be reproduced, forwarded or relied upon by any person other than the named recipient without our written consent.